## Roadmap Overview
OM-020 Implementation Roadmap
Sales Order Processing - SAP S/4HANA Implementation
Created: 08-Sep-2026 ¦ Project: Solventum
IMPLEMENTATION OVERVIEW
Total Duration | 12 weeks (3 phases)
Total Effort | 1,200 man-hours
Team Size | 8-12 resources
Number of Phases | 3 (Discovery, Configuration, Testing & Go-Live)
Parallel Workstreams | 4 (Config, Data Migration, Testing, Training)
Go-Live Date | Week 12 (End of Implementation)
SAP Modules | Sales & Distribution (SD), Finance (FI), Materials Management (MM)
Key Dependencies | Company Code, Plant, Sales Org, Material & Customer Masters
PROJECT TIMELINE
Phase 1: Discovery & Planning | Week 1-2 | Business requirement gathering, gap analysis
Phase 2: Configuration & Development | Week 3-8 | Master data setup, customization, integration
Phase 3: Testing & Go-Live | Week 9-12 | UAT, performance testing, cutover, training
Post-Implementation Support | Week 13+ | Stabilization, issue resolution, optimization

## Detailed Phases
Detailed Implementation Phases
PHASE 1: DISCOVERY & PLANNING (Week 1-2)
Task | Description | Duration | Owner | Deliverables
1.1 Kickoff Meeting | Project initiation, team alignment, scope review | 1 day | PM | Project Charter
1.2 Business Requirements | Document sales order processes, user needs, volumes | 3 days | BA | BRD Document
1.3 Current State Analysis | Analyze legacy system, existing configurations | 3 days | Functional Lead | As-Is Process
1.4 Gap Analysis | Identify fit/gap between SAP standard & requirements | 2 days | Consultant | Gap Analysis Report
1.5 Master Data Audit | Review customer, material, vendor master data | 2 days | Data Lead | Master Data Audit
1.6 Configuration Planning | Plan all configurations for OM-020 | 2 days | Config Lead | Config Roadmap
1.7 Risk Assessment | Identify risks, mitigation strategies | 1 day | PM | Risk Register
PHASE 2: CONFIGURATION & DEVELOPMENT (Week 3-8)
Task | Description | Duration | Owner | Deliverables
2.1 Company Code Setup | Create company codes, chart of accounts | 3 days | Finance Lead | Company Code Config
2.2 Plant Configuration | Setup plants, storage locations, warehouses | 3 days | MM Lead | Plant Config
2.3 Sales Org Configuration | Create sales orgs, distribution channels, divisions | 4 days | SD Lead | Sales Org Config
2.4 Sales Area Setup | Define sales areas (Org + Channel + Division) | 2 days | SD Lead | Sales Area Setup
2.5 Customer Master Creation | Create customer master data (XD01) | 5 days | Data Migration | Customer Master
2.6 Material Master Creation | Create material master data (MM01) | 5 days | Data Migration | Material Master
2.7 Pricing Configuration | Setup pricing procedure, condition records | 4 days | SD Consultant | Pricing Config
2.8 Credit Check Setup | Configure credit limits, risk categories | 3 days | Credit Manager | Credit Config
2.9 Document Type Config | Create sales order types (OR, OT, OC) | 3 days | SD Lead | Document Types
2.10 Number Range Setup | Configure number ranges for orders | 1 day | Config Lead | Number Ranges
2.11 ATP Check Configuration | Setup availability check rules | 2 days | SD Lead | ATP Config
2.12 Customization Development | User exits, enhancements, validations | 10 days | ABAP Dev | Custom Code
2.13 Integration Setup | Configure interfaces with EWM, Finance | 5 days | Interface Dev | Integration Config
PHASE 3: TESTING & GO-LIVE (Week 9-12)
Task | Description | Duration | Owner | Deliverables
3.1 Unit Testing | Test individual configurations and customizations | 5 days | QA Lead | Unit Test Report
3.2 System Integration Test | End-to-end process testing (SIT) | 5 days | QA Lead | SIT Report
3.3 User Acceptance Test | Business user testing (UAT) | 7 days | Business Owner | UAT Report
3.4 Performance Testing | Load, stress, volume testing | 3 days | Performance Lead | Perf Report
3.5 Security Testing | Access control, data protection validation | 2 days | Security Officer | Security Report
3.6 UAT Defect Resolution | Fix identified issues and bugs | 5 days | Dev/Config Team | Defect Log
3.7 Data Validation | Validate migrated master data accuracy | 3 days | Data QA | Data Validation Report
3.8 Cutover Planning | Plan production cutover activities | 3 days | PM | Cutover Plan
3.9 Training Delivery | Conduct user training sessions | 5 days | Training Lead | Training Materials
3.10 Documentation | Create runbooks, procedures, FAQs | 5 days | Doc Lead | Documentation
3.11 Go-Live Prep | Final checks, production readiness | 3 days | PM | Go-Live Checklist
3.12 Production Cutover | Execute go-live, production turnover | 2 days | Operations | Go-Live Report
3.13 Post-Go-Live Support | Monitor, troubleshoot production issues | 14 days | Support Team | Issues Log

## Resource Plan
Implementation Resource Plan
RESOURCE REQUIREMENTS
Role | Count | Effort (weeks) | Phase 1 | Phase 2 | Phase 3 | Remarks
Project Manager | 1 | 12 | Full | Full | Full | Overall project leadership
Business Analyst | 2 | 10 | Full | Part | Part | Requirements, testing
SD Functional Lead | 1 | 12 | Full | Full | Full | Sales order configuration
Finance Lead (FI) | 1 | 8 | Part | Full | Part | Company code, GL setup
MM Lead | 1 | 8 | Part | Full | Part | Plant, material master
ABAP Developer | 2 | 10 | None | Full | Part | Custom code, enhancements
Data Analyst | 2 | 8 | Part | Full | Part | Master data migration
QA/Tester Lead | 2 | 8 | None | Part | Full | Testing execution
Trainer | 1 | 6 | None | Part | Full | User training
Technical Support | 2 | 12 | Part | Part | Full | Infrastructure, servers
Data Security Officer | 1 | 4 | Part | Part | Full | Security, compliance
Business Users (Super Users) | 3 | 10 | Full | Full | Full | UAT, training support
TOTAL EFFORT | 1,200+ man-hours

## Risks & Mitigation
Risk Assessment & Mitigation Strategy
Risk ID | Risk Description | Impact | Likelihood | Severity | Mitigation Strategy | Owner
R1 | Incomplete master data | High | High | Critical | Early data audit, migration validation, cleansing process | Data Lead
R2 | Scope creep | Medium | High | High | Strict change control, steering committee approval | PM
R3 | Resource unavailability | High | Medium | High | Backup resources, cross-training, clear role definition | PM
R4 | Tight timeline | High | High | High | Early start, parallel workstreams, efficient planning | PM
R5 | Technical issues/bugs | Medium | Medium | Medium | Thorough testing, contingency code review, buffer time | Dev Lead
R6 | User resistance | Medium | Medium | Medium | Early communication, training, super user program | Training Lead
R7 | Integration failures | High | Medium | High | Early interface testing, vendor involvement, documentation | Tech Lead
R8 | Data security breach | High | Low | Critical | Security scanning, access controls, encryption | Security Officer
R9 | Production cutover issues | High | Medium | High | Dry run, rollback plan, cutover team training | Ops Lead
R10 | Inadequate testing | Medium | Medium | High | Define test scenarios early, adequate resources | QA Lead

## Testing Strategy
Testing Strategy & Approach
TEST LEVELS
Test Level | Scope | Duration | Test Cases | Owner | Entry/Exit Criteria
Unit Test (UT) | Individual configs, custom code | 5 days | 50+ | Developer | Code complete → Defects <5%
System Integration Test (SIT) | OM-020 end-to-end process | 5 days | 100+ | QA Lead | UT complete → 95%+ pass rate
User Acceptance Test (UAT) | Business user validation | 7 days | 150+ | Business Owner | SIT complete → Business sign-off
Performance Test | Load, stress, scalability | 3 days | 20+ | Performance Lead | All UAT passed → Acceptable response times
Security Test | Access control, compliance | 2 days | 25+ | Security Officer | All tests passed → Zero vulnerabilities
Regression Test | Impact on other modules | 3 days | 75+ | QA Lead | Changes integrated → No new defects
TEST SCENARIOS FOR OM-020
Scenario | Test Case | Expected Result | Priority
Create Sales Order | SO-TC01: Create standard SO with valid customer & material | Order created, auto-numbered, saved | Critical
Credit Check | SO-TC02: Create SO for customer exceeding credit limit | Order blocked with warning/error | Critical
Availability Check | SO-TC03: Create SO for out-of-stock material | Order created with partial availability | High
Pricing | SO-TC04: Create SO with volume discount applicable | Correct discount applied, price calculated | Critical
Delivery Creation | SO-TC05: Post SO, verify delivery auto-created | Delivery created with correct items | High
Rush Order | SO-TC06: Create rush order with expedited delivery | Rush order type applied, priority set | Medium
Cash Sale | SO-TC07: Create cash sales order without customer master | Immediate payment captured, order saved | Medium
Order Modification | SO-TC08: Modify saved order (quantity, delivery date) | Changes allowed per status rules | High
Order Cancellation | SO-TC09: Cancel active sales order | Order status changed to cancelled | Medium
Reporting | SO-TC10: Generate sales order aging report | Report shows all active orders by date | Medium
Multi-location | SO-TC11: SO for customer with multiple bill-to/ship-to | Correct addresses used for delivery | High

## Go-Live Checklist
Go-Live Readiness Checklist
PRE-GO-LIVE VERIFICATION
Item | Verification | Status | Responsible
Configuration | All OM-020 configurations reviewed & approved | ☐ | Config Lead
Master Data | Customer, material, pricing data validated & complete | ☐ | Data Lead
Testing | UAT completed with 100% pass rate | ☐ | QA Lead
Customization | All custom code deployed to production | ☐ | Dev Lead
Documentation | Procedures, runbooks, FAQs finalized & available | ☐ | Doc Lead
Training | All users trained and certified | ☐ | Training Lead
Cutover Plan | Detailed cutover plan with rollback procedures | ☐ | PM
Backups | Production backups created & verified | ☐ | Ops Lead
Performance | Performance testing passed with acceptable metrics | ☐ | Perf Lead
Security | Security scan passed, access controls validated | ☐ | Security Officer
Interfaces | All integrations tested end-to-end | ☐ | Tech Lead
Escalation | Escalation matrix & support team briefed | ☐ | PM
Communication | All stakeholders notified of go-live date/time | ☐ | PM
Contingency | Contingency & rollback plans documented | ☐ | PM
GO-LIVE DAY ACTIVITIES
Time | Activity | Owner | Duration | Approver
T-24hrs | Final UAT validation, confirm production readiness | QA Lead | 2 hours | PM
T-4hrs | Final backup creation & verification | Ops Lead | 1 hour | Tech Lead
T-2hrs | User communication: go-live notification sent | PM | 0.5 hours | PM
T-1hr | Team stand-by, war room setup, escalation ready | All Teams | 1 hour | PM
T+0 | Cutover activities start: disable legacy systems | Ops Team | 1 hour | Tech Lead
T+1hr | Data migration run, validation | Data Team | 2 hours | Data Lead
T+3hrs | Production system startup & smoke testing | Ops/QA | 1 hour | Tech Lead
T+4hrs | System available to users with support active | All Teams | Ongoing | PM
T+24hrs | First post-go-live review meeting | PM | 1 hour | PM

## Training Plan
User Training & Change Management Plan
TRAINING APPROACH
Training Track | Audience | Duration | Format | Timing | Deliverables
Super User Training | Key business users, power users (15-20 people) | 3 days | Instructor-led + hands-on lab | Week 11 | Training materials, certifications
End User Training | All sales order processors (100-150 people) | 2 days | Classroom sessions + online | Week 11-12 | Quick reference guides, FAQs
Management Training | Sales managers, supervisors (20-30 people) | 1 day | Executive overview | Week 11 | Executive summary, dashboards
IT Support Training | Support team, IT helpdesk (5-8 people) | 2 days | Technical deep dive | Week 10 | Troubleshooting guide, configuration details
Finance Training | Finance users, cost center owners (10-15 people) | 1 day | Financial integration overview | Week 11 | Finance guide, reporting procedures
KEY TRAINING TOPICS FOR OM-020
Topic | Details | Audience
Introduction to OM-020 | Business process overview, key features, benefits | All users
Creating Sales Orders | Step-by-step: VA01 transaction, required fields, validations | Sales team
Order Types | Standard, rush, cash sales - when to use each type | Sales team
Credit Management | Credit check, approval, exceptions, hold procedures | Credit team
Pricing & Discounts | How pricing is calculated, discount rules, overrides | Sales team
Availability Check | ATP check, partial availability, delivery scheduling | Sales team
Order Modification | What can be changed post-creation, limitations | Sales team
Reporting | Available reports, custom reports, scheduling | Managers
Troubleshooting | Common errors, how to resolve, escalation path | Support team
Integration Points | How OM-020 connects to delivery, billing, finance | All users